## Sprint 2
Sprint #1Tracking Sheet
|  | Project | Group 6: Bookstore Management System
|  | Sprint # | 1
|  | Start date | 2025-05-19
|  | End date | 2025-06-01
|  |  | Total Team Members | 4
[5 empty] | week 1 | [6 empty] | week 2
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Task ID | Story ID | Description | Responsibility | Initial estimate (hrs) | 0 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12
T-1 | N/A | Conduct Sprint Standup | Scrum Master | 1
T-2 | US-11 | Perform Supplier Order | Developer 1 | 6
T-3 | US-12 | Customer Order | Developer 1 | 3
T-4 | US-13 | Wishlist Button | Developer 1 | 2
T-5 | US-14 | Book Recommendations | Developer 1 | 2
T-6 | US-15 | Web Interface | Developer 1 | 8
T-7 | US-16 | Audit Log | Developer 2 | 2
T-8 | US-17 | View Sales Records | Developer 2 | 2
T-9 | US-18 | Create Report Templates | Developer 2 | 4
T-10 | US-19 | Membership | Developer 2 | 4
T-11 | US-20 | Customer Reviews | Developer 2 | 2
T-12
T-13
T-14
T-15
T-16
|  | Remaining units (actual) |  | 64
|  | Remaining units (ideal) |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[5 empty] | 59.4286 | 54.8571 | 50.2857 | 45.7143 | 41.1429 | 36.5714 | 32 | 27.4286 | 22.8571 | 18.2857 | 13.7143 | 9.1429 | 4.5714 | 2.1316e-14
[10 empty] | 0 | 36 | [5 empty] | 0 | 0
[10 empty] | 10 | 0 | [5 empty] | 10 | 0

## Sprint 1
Sprint #1Tracking Sheet
|  | Project | Group 6: Bookstore Management System
|  | Sprint # | 1
|  | Start date | 2025-05-06
|  | End date | 2025-05-18
|  |  | Total Team Members | 4
[5 empty] | week 1 | [6 empty] | week 2
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Task ID | Story ID | Description | Responsibility | Initial estimate (hrs) | 0 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12
T-1 | N/A | Conduct Sprint Standup | Scrum Master | 1
T-2 | US-1 | Inventory Management | Developer 1 | 4 | 1900-01-01: 2; 1900-01-02: 2; 1900-01-05: 2
T-3 | US-2 | Search Inventory | Developer 1 | 2 | 1900-01-02: 2
T-4 | US-3 | Filtering Inventory | Developer 1 | 2 | bar: 1900-01-03
T-5 | US-4 | Security Inventory | Developer 1 | 2 | 1900-01-04: 2
T-6 | US-5 | Add Books to Inventory | Developer 1 | 2 | 1900-01-05: 2
T-7 | US-6 | View Sales Records | Developer 2 | 4
T-8 | US-7 | Book Status Update | Developer 2 | 2 | 1900-01-04: 2
T-9 | US-8 | Point of Sale Interface | Developer 2 | 4 | 1900-01-01: 3; 1900-01-03: 1
T-10 | US-9 | Log Sales Records | Developer 2 | 2 | 1900-01-02: 0
T-11 | US-10 | Payment Encryption | Developer 2 | 6 | 1900-01-02: 0
T-12 | n/a | Week 1 Progress | All | 8 | 1900-01-03: 2; 1900-01-04: 1; 1900-01-05: 3; 1900-01-06: 2
T-13
T-14
T-15
T-16
|  | Remaining units (actual) |  | 64
|  | Remaining units (ideal) |  |  | #N/A | #N/A | #N/A | 55 | 51 | 46 | 39 | 37 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[5 empty] | 59.4286 | 54.8571 | 50.2857 | 45.7143 | 41.1429 | 36.5714 | 32 | 27.4286 | 22.8571 | 18.2857 | 13.7143 | 9.1429 | 4.5714 | 2.1316e-14
[10 empty] | 0 | 39 | [5 empty] | 0 | 7
[10 empty] | 10 | 0 | [5 empty] | 10 | 0

## Product Backlog
PRODUCT BACKLOG: Group 2: Bookstore Management System
| Organizations | Colorado Technical University CS492: CS Team Project 2, Group 2
| Project | Bookstore Management System
| Product Owner | Kyle Spicer
| Scrum Master | Ryan Kraft
| Development Team | Shaun White, Michael Oneal
Story ID | Title | Description | Acceptance Criteria | Priority # | Sprint # | Responsibility
US-1 | Inventory Management | As a developer, I want to be able to interact with the bookstore inventory database. | Able to connect, read, and update records in the inventory database without errors. | 1 | 1
US-2 | Search Inventory | As a user, I want to be able to search the bookstore inventory. | Users can search books by title, author, or ISBN and get accurate results within 2 seconds. | 1 | 1
US-3 | Filtering Inventory | As a user, I want to be able to filter inventory from preference (genre, name, etc.) | Users can filter inventory by genre, author, price range, and stock status. | 1 | 1
US-4 | Security Inventory | As an owner, I want to ensure the bookstore inventory is only accessed/altered by proper personnel | Only authenticated users with inventory roles can add/edit inventory. Unauthorized users are blocked. | 1 | 1
US-5 | Add Books to Inventory | As an owner, I want to be able to add new books to inventory. | Owner can input new book details and see them reflected in the inventory within 1 minute. | 1 | 1
US-6 | View Sales Records | As an owner, I want to be able to view all sales transactions | Owner can retrieve sales logs by date range and transaction ID. | 1 | 1
US-7 | Book Status Update | As an owner, I want the database to inform customer of availability. Example "Unavailable" when quatity reaches 0. | System shows “Unavailable” if quantity = 0 and updates stock status in real-time after purchases. | 1 | 1
US-8 | Point of Sale Interface | Notification of sale system. | On completing a sale, the system reduces stock, logs sale, and shows confirmation message. | 1 | 1
US-9 | Log Sales Records | As an owner, I want all sales transaction to be logger and produce a receipt. | Each sale generates a unique receipt ID, logs date, item, quantity, and total. | 1 | 1
US-10 | Payment Encryption | As a customer, I want to be able to securely purchase products from the bookstore | All payment transactions are encrypted with industry-standard protocols (e.g., TLS 1.2+). | 1 | 1
US-11 | Perform Supplier Order | As an owner, I want low inventory to place a supplier order | When stock reaches reorder level, owner is notified and can submit a supplier order. | 2 | 2
US-12 | Customer Order | As a developer, I want to provide an intuitive interface for customers to interact | Customers can browse, select books, and place an order with confirmation within 3 steps. | 2 | 2
US-13 | Wishlist Button | As a customer, I want to be able to maintain a list of books I would like. Like amazon wishlist. | Customers can add/remove books to/from wishlist and view wishlist anytime when logged in. | 2 | 2
US-14 | Book Recommendations | As a customer, I want to see recommendations for books based on previous orders | Recommendations appear on home page based on at least 3 past customer orders. | 2 | 2
US-15 | Web Interface | As an owner and customer, I want to be able to interact with the bookstore through a friendly web interface. | Both owners and customers can log in and perform tasks with mobile-responsive web pages. | 2 | 2
US-16 | Audit Log | As an owner, I want to be able to view my staff's interaction with the bookstore management system | Owner can view staff actions (additions, edits, deletions) in audit trail with timestamps. | 2 | 2
US-17 | View Sales Records | As an owner, I want to be able to view all sales transactions | Owner can retrieve and filter sales records similar to US-6 (de-duplicate or merge with US-6). | 2 | 2
US-18 | Create Report Templates | As an owner, I want to be able to view the trends of books that are selling or not selling. | Owner can select date ranges and generate reports showing top-selling and low-selling books. | 2 | 2
US-19 | Membership | As a customer, I want to be able to securely log on and use the bookstore management system. | Customers can create accounts, log in securely, and manage personal information. | 2 | 2
US-20 | Customer Reviews | As a customer, I want to be able to leave reviews for products. | Logged-in customers can leave star ratings and written reviews for books they purchased. | 2 | 2

## Introduction
Group 2: Bookstore Management System
What is this? | This workbook is meant to help manage and prioritize the user stories and features using scrum.
How to use and read this document? | Before project start: The product owner is responsible for managing and maintaining the product backlog of user stories.
Before each sprint: The vendor will break down the user stories into tasks.
Notes | Cells that you can edit have a blue background.
Sprints are assumed to be 2 weeks long (10 working days)/
Licence | This work is licensed under a Creative Commons Attribution-Share Alike 3.0 Unported License.
Origins | This work is inspired by the Scrum Template published by Nicolas Martignole on his "Touilleur Express" blog. Adapted by Olivier Gérardin.