## Sprint 2
Sprint #1Tracking Sheet
|  | Project | Group 6: Bookstore Management System
|  | Sprint # | 1
|  | Start date | 2025-05-06
|  | End date | 2025-05-18
|  |  | Total Team Members | 4
[5 empty] | week 1 | [6 empty] | week 2
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Task ID | Story ID | Description | Responsibility | Initial estimate (hrs) | 0 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12
T-1
T-2
T-3
T-4
T-5
T-6
T-7
T-8
T-9
T-10
T-11
T-12
T-13
T-14
T-15
T-16
|  | Remaining units (actual) |  | 64
|  | Remaining units (ideal) |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[5 empty] | 59.4286 | 54.8571 | 50.2857 | 45.7143 | 41.1429 | 36.5714 | 32 | 27.4286 | 22.8571 | 18.2857 | 13.7143 | 9.1429 | 4.5714 | 2.1316e-14
[10 empty] | 0 | 0 | [5 empty] | 0 | 0
[10 empty] | 10 | 0 | [5 empty] | 10 | 0

## Sprint 1
Sprint #1Tracking Sheet
|  | Project | Group 6: Bookstore Management System
|  | Sprint # | 1
|  | Start date | 2025-05-06
|  | End date | 2025-05-18
|  |  | Total Team Members | 4
[5 empty] | week 1 | [6 empty] | week 2
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Task ID | Story ID | Description | Responsibility | Initial estimate (hrs) | 0 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12
T-1
T-2
T-3
T-4
T-5
T-6
T-7
T-8
T-9
T-10
T-11
T-12
T-13
T-14
T-15
T-16
|  | Remaining units (actual) |  | 64
|  | Remaining units (ideal) |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[5 empty] | 59.4286 | 54.8571 | 50.2857 | 45.7143 | 41.1429 | 36.5714 | 32 | 27.4286 | 22.8571 | 18.2857 | 13.7143 | 9.1429 | 4.5714 | 2.1316e-14
[10 empty] | 0 | 0 | [5 empty] | 0 | 0
[10 empty] | 10 | 0 | [5 empty] | 10 | 0

## Product Backlog
PRODUCT BACKLOG: Group 2: Bookstore Management System
| Organizations | Colorado Technical University CS492: CS Team Project 2, Group 2
| Project | Bookstore Management System
| Product Owner | Kyle Spicer
Scrum Master
Development Team
Story ID | Title | Description | Acceptance Criteria | Priority # | Sprint # | Responsibility

## Introduction
Group 2: Bookstore Management System
What is this? | This workbook is meant to help manage and prioritize the user stories and features using scrum.
How to use and read this document? | Before project start: The product owner is responsible for managing and maintaining the product backlog of user stories.
Before each sprint: The vendor will break down the user stories into tasks.
Notes | Cells that you can edit have a blue background.
Sprints are assumed to be 2 weeks long (10 working days)/
Licence | This work is licensed under a Creative Commons Attribution-Share Alike 3.0 Unported License.
Origins | This work is inspired by the Scrum Template published by Nicolas Martignole on his "Touilleur Express" blog. Adapted by Olivier Gérardin.

## OLD REFERENCE Product backlog
PRODUCT BACKLOG: Group 6: Bookstore Management System
| Organizations | Colorado Technical University CS491: CS Team Project 1, Group 6
| Project | Bookstore Management System
| Product Owner | Kyle Spicer
| Scrum Master | Kyle Spicer
| Development Team | Alyiah Savoy, Cody Sullivan
Story ID | Title | Description | Acceptance Criteria | Priority # | Sprint # | Responsibility
US-10 | CLI Design | As a developer, I want a modular CLI so that features are easy to access. | Commands are logically grouped. Help documentation is available. CLI is testable and modular. | 1 | 1 | Developer 1 + 2
US-1 | Catalog Books | As a manager/owner, I want to catalog books so I can track and update inventory. | Books can be added, edited, and removed from database. Data is saved to JSON or CSV files. Input is validated. | 2 | 1 | Developer 1
US-2 | View Inventory | As a manager/owner, I want to query/view real-time inventory so I can manage stock. | Current inventory is listed and correct. Accurate data is displayed after updates. Only authorized users have access. | 2 | 1 | Developer 2
US-7 | Data Persistence | As a developer, I want data to persist using JSON files. | JSON or CSV files are updated correctly. Format is consistent. Errors are handled securely. Backup/restore functionality exists for data loss scenarios. | 3 | 1 | Developer 1 + 2
US-9 | TCP Server | As a developer, I want a multithreaded TCP Server. | Server accepts multiple client connections. Sessions are isolated and cleaned up. Threading is managed safely. | 3 | 1 | Developer 1 + 2
US-3 | Record Sales | As a manager/owener, I want all sales properly recorded for accounting purposes. | Sales are automatically logged. Data includes item, price, and timestamp. Data is stored securely in JSON or CSV file. Only authorized users can trigger recording actions. | 1 | 2 | Developer 1
US-4 | Place Customer Orders | As a customer, I want to place book orders online. | Orders can be created and viewed. Stock is updated on order. Data is transmitted securely. Data includes customer/supplier ID, item, and timestamp. | 1 | 2 | Developer 2
US-6 | User Roles and Authentication | As a system user, I want to log in with a role. | Login interface prompts for credentials / role. Access to certain features are role-restricted. Credentials are stored securely. Failed login attempts are logged. | 2 | 2 | Developer 2
US-5 | Place Supplier Orders | As a manager/owner, I want to order books from suppliers. | Supplier orders can be created. Confirmation of orders is logged. Role restricted access is enforced. Data includes customer/supplier ID, item, and timestamp. | 3 | 2 | Developer 1
US-8 | Sales Reporting | As a manager, I want reports of sales and stock. | Reports show total revenue. Inventory alerts for low stock level. Secure access only | 3 | 2 | Developer 2
E1 | View and manage inventory | Monitor, update, and manage book inventory in real-time. | The system will keep track and diplay inventory count for all books. | High | 1 | Developers, Scrum Master
E1.1 | Receive Stock-Alerts | Monitor and update stocks. | The system will notify management when stock is either low or unavailable. | Medium | 1 | Developers
E2 | Track Payment Methods | Automatically record and store transactional and payment data for reporting and accounting purposes. | Report accurately displays all transactions details and is allowed to be filtered. | Medium | 1 | Developers, Scrum Master, Product Owner
E2.1 | Generate Sales Record | View daily, weekly, and monthly reports or trends to analyze performance and sales. | Report displays charts or graphs depending on the selection: daily, weekly, or monthly view. | Low | 1 | Developers, Scrum Master, Product Owner
E3 | Place Bulk Orders | Enable the bookstore to place and manage orders with book suppliers. | Bookstore employee can search, select, and place (bulk) orders with manufactuerers. | Medium | 2 | Developers, Scrum Master
E4 | Browse and Place Orders | Allow customers to browse available inventory and place orders. | Bookstore customers can search, select, and add books to cart. Customer should be able to complete payment using a secure link. | High | 2 | Developers, Scrum Master, Product Owner
E4.1 | View Order Status | Allow customers to track their placed orders. | The customer can track their order to receive real-time status updates. | Medium | 2 | Developers, Scrum Master

## OLD REFERENCE Sprint 1
Sprint #1Tracking Sheet
|  | Project | Group 6: Bookstore Management System
|  | Sprint # | 1
|  | Start date | 2025-04-05
|  | End date | 2025-04-19
|  |  | Total Team Members | 4
[5 empty] | week 1 | [6 empty] | week 2
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Task ID | Story ID | Description | Responsibility | Initial estimat (hrs) | 0 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12
8 | N/A | Scrum Meeting (discuss 3.0, and 3.1) | ALL | 1
T-1 | US-10 | Design CLI structure and command groups | Developer 1 + 2 | 4
T-2 | US-10 | Implement CLI help docs | Developer 1 | 2
T-3 | US-10 | Make CLI testable and modular | Developer 2 | 4
T-4 | US-1 | Implement reading in CSV file for book database | Developer 1+2 | 4
T-5 | US-1 | Implement add/edit/remove book function | Developer 1 | 3
T-6 | US-1 | Validate input for book entries | Developer 2 | 2
T-7 | US-2 | Secure inventory listing view with user access checks | Developer 1 | 2
T-8 | US-2 | Implement inventory listing | Developer 1 | 3
T-9 | US-7 | Set up JSON persistence module | Developer 1 + 2 | 4
T-10 | US-7 | Implement backup/restore functionality | Developer 1 | 3
T-11 | US-9 | Design TCP Server architecture | Developer 1 + 2 | 4
T-12 | US-9 | Implement multithreading and session management | Developer 1 + 2 | 4
T-13 | US-9 | Secure and clean up server sessions | Developer 2 | 3
T-14 | NA | Sprint Planning Meeting | All | 1
T-15 | NA | Sprint Demo & Retrospective prep | All | 2
T-16 | NA | Setup GitHub and CI/CD pipeline | Developer 1 + 2 | 4
8 | N/A | Scrum Meeting (discuss 3.0, and 3.1) | ALL | 1
|  | Remaining units (actual) |  | 64 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | Remaining units (ideal) |  |  | 59.4286 | 54.8571 | 50.2857 | 45.7143 | 41.1429 | 36.5714 | 32 | 27.4286 | 22.8571 | 18.2857 | 13.7143 | 9.1429 | 4.5714 | 2.1316e-14
[10 empty] | 0 | 50 | [5 empty] | 0 | 0
[10 empty] | 10 | 0 | [5 empty] | 10 | 0

## OLD REFERENCE Sprint 2
Sprint #2Tracking Sheet
|  | Project | Group 6: Bookstore Management System
|  | Sprint # | 2
|  | Start date | 2025-04-19
|  | Start date | 2025-05-03
|  |  | Total Team Members | 4
[5 empty] | week 1 | [6 empty] | week 2
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Task ID | Story ID | Description | Responsibility | Initial estimat (hrs) | 0 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12
8 | N/A | Scrum Meeting (discuss 3.0, and 3.1) | ALL | 1
T-17 | US-3 | Implement sales recording mechanism | Developer 1 | 4
T-18 | US-3 | Store sales data securely with validation | Developer 1 | 3
T-19 | US-4 | Implement customer order creation & tracking | Developer 2 | 4
T-20 | US-4 | Secure data transfer for order processing | Developer 2 | 2
T-21 | US-5 | Implement supplier ordering logic | Developer 1 | 4
T-22 | US-5 | Confirm and log supplier order transactions | Developer 1 | 3
T-23 | US-6 | Design login interface and role selection | Developer 2 | 3
T-24 | US-6 | Implement access control per role | Developer 2 | 3
T-25 | US-6 | Securely store credentials and log failures | Developer 1 | 3
T-26 | US-8 | Build reporting module for sales and inventory | Developer 1 | 4
T-27 | US-8 | Implement secure access for reporting | Developer 2 | 2
T-28 | NA | Sprint Planning Meeting | All | 1
T-29 | NA | Sprint Demo & Retrospective prep | All | 2
8 | N/A | Scrum Meeting (discuss 3.0, and 3.1) | ALL | 1
|  | Remaining units (actual) |  | 64 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | Remaining units (ideal) |  |  | 59.4286 | 54.8571 | 50.2857 | 45.7143 | 41.1429 | 36.5714 | 32 | 27.4286 | 22.8571 | 18.2857 | 13.7143 | 9.1429 | 4.5714 | 2.1316e-14
[10 empty] | 0 | 39 | [5 empty] | 0 | 0
[10 empty] | 10 | 0 | [5 empty] | 10 | 0